## Checklist
Level 1 | Level 2 | Level 3 | Notes
Organize Your Team
Identify the Product Owner, who will oversee the project to make sure it meets stakeholders' vision.
Identify the Scrummaster, or Project Manager, who will guide the technical team day-to-day.
Identify 3-5 developers who will form your team and carry out the work of the project.
Organize Your Project
Meet with the Product Owner and stakeholders to agree on the vision and scope of the project.
Work with the Product Owner to develop a set of User Stories, or features, that will achieve the project vision.
Build the Product Backlog, or catalog of features to be developed, from the User Stories.
Work with the development team to estimate how long each task will require for completion.
Prioritize the work items in the Product Backlog, emphasizing riskier tasks and must-have features first.
Decide on the length of each Sprint, or development iteration.
Plan tasks to be completed in the each Sprint, beginning with the highest priority items, and taking into account task estimates and available development time.
Manage Your Project
Hold a short (20-minute) daily Scrum, or status meeting, with your development team.
During the Scrum, ask each team member to report three status points:
What tasks he or she worked on the day before.
What tasks he or she plans to work on that day.
What obstacles he or she faces in completing assigned tasks.
What tasks he or she worked on the day before.
What tasks he or she plans to work on that day.
What obstacles he or she faces in completing assigned tasks.
Do not change priorities or work items a Sprint.
Meet with the Product Owner at the end of each Sprint to re-prioritize remaining items in the Product Backlog and to plan the next Sprint.
Build Your Toolset
Choose a calendar application that can be shared by the Scrummaster, the Product Owner, and the development team.
Publish the project timeline to the calendar.
Choose a task-tracking application for building your Product Backlog and managing work items within your Sprints.
Choose a method for sharing files among team members, the Scrummaster, and the Product Owner.
Build an email list for communicating among project members.
© Checklist.com 2010-2024
https://checklist.com/agile-project-management-checklist