## Checklist
Level 1 | Level 2 | Notes
Build An Oversight Committee
| Upper Management | At least one high-level manager to give you executive input and buy-in.
| Unit Managers | For departmental input and prioritization.
| Information Technology | Guidance for high-level technical decisions.
| Vendor Management | Committee member who communicates directly with any related vendors.
| Impartial Party | Someone who is not directly involved with implementation, for improved perspective.
| Customer Advocate | Represents customer concerns in strategic decisions.
| Legal Counsel | Helps to make sure that your new site does not set you up for legal problems.
Assemble Your Implementation Team
| Project Manager | A team leader who can talk to various parties and drive the project.
IT. Key IT staff members who are vital to resolving technical issues and integrating systems.
| Content Managers | Business unit experts who will develop the individual CMS pages and posts.
| Web Designer | Someone with an eye for detail and aesthetics to make your website appealing and user-friendly.
| Vendor | Maintain regular contact with your CMS vendor contact for training and guidance.
Build Your Project Plan
| Structure | How will you run your project? Waterfall? Scrum?
| Scope | Determine the overall goals of your CMS implementation project.
| Backlog | Build a catalog of all known tasks that need to be completed.
| Estimate | Develop a rough idea of how long each task will require to complete.
| Risk assessment | Determine which tasks are foundational to success and prioritize them first.
| Prioritize | Determine the relative importance and risk of remaining tasks.
| Organize | Group tasks to be done by related functionality and to fit into your implementation time blocks.
| Communication | Decide how and when you will communicate with project stakeholders.
| Progress tracking | Agree on mechanisms for tracking project progress.
Develop Your CMS Implementation Schedule
| Target | When do you need to have the entire project completed?
| Start | When can work on CMS implementation begin?
| Milestones | What major tasks do you need to have completed by which dates to stay on track?
| Fill the calendar | Complete your schedule with grouped, prioritized tasks until all available time is filled.
| Re-evaluate | Are there tasks that did not fit into your schedule? Do you need to re-prioritize?
| Publish | Make the implementation schedule available to all members of the implementation team and oversight committee.
Develop Your Content Management Policy
| Access | Who will be allowed to create content on the new site?
| Design | What design standards with content creators need to follow?
| Appropriate use | What type of content is appropriate (or not appropriate) for the site?
| Images | What types and sources of images will be used on your site?
| Social media | Will you include social media components in your site content?
Deliver the Content Management System Implementation
| Build | Complete the foundational, high-risk tasks.
| Evaluate | Does the foundation function as you expected?
| Implement features | Build on the CMS foundation by completing other tasks in priority order.
| Test | Does your site perform correctly, and does it look the way you want?
| Track progress | Meet regularly with the implementation team to make sure that you are on track.
| Report | Meet regularly with the oversight committee to report progress and get feedback.
| Refine | Adjust your project plan as organizational priorities shift.
| Policy | Review and adjust content policy as your site takes shape.
| Train | Engage administrative users to make sure they can use the new CMS efficiently.
© Checklist.com 2010-2024
https://checklist.com/content-management-system-implementation-checklist