## Checklist
Level 1 | Level 2 | Notes
6 to 12 months before
| Goal | Determine the purpose of your event. The purpose is very important, as it determines the kind of activities you can organize for your event.
| Theme | If using a theme, make sure that it coincides with the values of your organization. Avoid cliches that will not attract guests or media coverage.
| Space | If you need to hold the event outside of your business space, start looking early. A strong purpose statement will help you determine the kind of space you will need.
| Management | Appoint an official general manager for the event. Whether it is yourself or someone else, a clear chain of command has to be set.
| Committees | After appointing the general manager, start building committees for the different aspects of the event. Breaking down the planning for big events is usually a good idea.
| Quotes | Get estimates from your usual or potential providers. The budget committee will need these to build their financial projections.
| Event Entertainment | If your event has an artistic component, request quotes from well-known artists or have auditions early in the planning.
| Sponsorships | If you will solicit sponsorships, work on the sponsorship resume right away. Potential sponsors will want to know the different sponsorship levels quite early, and it will also help with budgeting.
| Budget | While waiting for quotes and sponsors, build a preliminary budget. It can be modified throughout the planning stages.
| Permits and licenses | Check if you need any kind of permit or license around your event, especially if you plan on serving alcohol.
| Cover charge | If you will charge an admission price, determine the amount with the budget committee.
| Date | Finalize the date within the first three months of planning. This will help with coordinating artists, suppliers and other elements of your event without the risk of conflicts.
| Stationery | Meet with a graphic designer (in-house or consultant) and start drafting the different printed documents you will require for your event.
| Early printing | Hire a printer for invitations, reminders and sponsorship requests.
| Public relations | Meet with your relationist and build a preliminary timeline for publicity and media relations.
| Photography | If you need any pre-event and publicity photos taken, hire a photographer and take these as soon as you can.
3 to 6 months before
| Committees | Organize regular committee meetings and have them provide weekly reports to the general manager.
| Sponsorships | Start mailing sponsorship and donation request to potential sponsors and donors.
| Logos | Request company logos from confirmed sponsors to go on the next printed documents.
| Design | Have your graphic designer confirm the templates for all future printed documents.
| Printing | After finalizing the designs with your graphic designer, send your next printing orders to the printer.
| Ticketing | If your event will use tickets, have them printed at this time also, and make them available for distribution.
| Guest list | Build a final guest list, and mail invitations and other documentation to them.
| Entertainment | After confirming with your entertainers, sign a contract with them.
| Posters | Send out people throughout your city to look for potential locations for posters. Have them report on space availability.
| Media | Meet with your relationist and make appointments for interviews and other media coverage.
| Food | After choosing a caterer and signing a contract with them, choose the menu with them. Provide choices for different dietary requirements.
| Licenses | At this time, you should request the different permits and licenses you will need.
| Insurance | Do not forget to get liability insurance for your event; sometimes organization insurance does not cover these kinds of events.
1 month before
| Tickets | Check the ticket sales. Follow up with invited guests who have not yet responded.
| Publicity | Reserve your publicity with radio and television stations as well as with printed media.
| Staffing | If you require extra staff for the event, start advertising the positions now or go to an employment agency for help.
| Space | Draw room diagrams and plan the seating, or whatever combination of space and tables you have.
| Catering | By this time, you should have a good idea of how many guests will come; you should provide this number to your caterer so he can plan accordingly. Request a final quote from your caterer and sign a contract.
| Timeline | If your event involves a sequence of presentations or entertainment, write down the timeline. Give the scripts to the participants, request comments and work through potential problems.
| Security | Hire a security agency to estimate your security needs.
1 week before
| Committees | Meet with your committees one last time. Solve last-minute problems.
| Guests | Confirm final guestlist and attendance numbers.
| Staff | Organize preliminary staff meeting to explain tasks and confirm availability. Hire new staff right away if necessary.
| Timeline | Send final timeline to the participants.
| Catering | Confirm your final order with your caterer.
| Publicity | Meet with journalists or media stations to finalize media coverage details.
| Rehearsal | Plan rehearsals as needed throughout the week.
| Payments | Have accounting write any cheques that need to be handed out on the day of the event.
The day before
| Clothes | Choose your attire for the event, and have a change of clothes ready, just in case.
| Providers | Confirm delivery times with all your providers, and verify any previously delivered items.
The day of the event
| Arrival | Get to the event space early and supervise deliveries.
| Inventory | Make an inventory of all supplies and make sure you have everything you need.
| Staff | Put your staff in position and confirm their tasks.
| Light and sound | Check with your technicians for any potential problems with the technical setup.
| Rehearsal | Hold a final rehearsal a few hours before the event, and check the sound and lighting at the same time.
| Enjoy the event and remember to relax | You've planned well and everything will work perfectly.
Post-event
| Payments | Remember to pay any outstanding invoices.
| Final reports | Request final reports from the committees, as well as a final budget.
© Checklist.com 2010-2024
https://checklist.com/corporate-event-planning-checklist