## Checklist
Level 1 | Level 2 | Notes
6 to 12 months in advance:
| Purpose | Choose the purpose of the event. Is it a celebration, a fundraiser, or something else? This will influence the kind of event you will hold.
| Theme | Choose a theme that is relevant, but also interesting. Cliche themes won't attract many guests.
| Site | Look around for places that can hold the event. Meet with potential space providers.
| Manager | You might need to appoint someone, or yourself, as event manager.
| Committees | Build committees if they are required. With a big enough event, you might need several of them and need to appoint a chair for each.
| Estimates | Get estimates for food, drinks, space and rental equipment. This will help with budgeting.
| Event entertainment | If providing artistic entertainment, hire well-known entertainers or hold auditions.
| Sponsorships | Determine if you will require sponsorships. Build a sponsorship sheet, with the different levels, so that potential sponsors know right away at what level they want to participate.
| Budget | Get an initial budget from the financial committee. This step is very important.
| Licences | Check if you need any kind of permit or license to hold an event or serve alcohol.
| Proposals | Review proposals for decorations and printing.
| Admission | If charging a cover, decide the price.
| Mailing list | Build a mailing list with potential guests or businesses to contact.
| Date | Choose a final date and check for conflicts with your providers.
| Designer | Choose your graphic designer and draft the documentation and invitations.
| Printing | Order the printing for invitations, hold-the-date reminders and other early stationery.
| Marketing | Build your marketing timeline with your public relations specialist.
Reserve your professional photographer and have any pre-event photos taken.
3 to 6 months in advance:
| Committees | Hold committee meetings regularly, and request reports.
| Funding | Send your requests for funding to your potential donors.
| Sponsors | Ask your confirmed sponsors for their logos for publicity printing.
| Stationery | Meet with your graphic designer and confirm the design for all printed material.
| Printing | Order the printing for posters and other stationery after the design is finalized.
| Tickets | If required, have the admission tickets printed and ready for distribution.
| Mailing list | Write down the final mailing list for guests, and print the letters or send the emails.
| Contracts | Sign the contracts with the entertainers.
| Posters | Build a list of potential poster locations. Send out people to verify the availability of space.
| Public relations | Plan your publicity and interviews with television and radio stations, and printed media.
| Catering | If serving food, build the menu with your caterer. Make sure you consider the dietary requirements of your guests.
| Permits | Request permits from your municipality if required.
| Insurance | Sign an insurance contract with your insurer.
| Celebrities | Confirm celebrity participation in writing.
2 months in advance:
| Pre-event party | Organize a party that coincides with the sending of invitations.
| Invitations | Write personal notes for the invitations and have them mailed.
| Posters | Have your posters distributed and placed at previously chosen locations.
| Accommodations | Reserve accommodations for your VIPs, if required.
| Transportation | Arrange transportation for your VIPs, if required.
| Media | Confirm the presence of the media at your event. Assign journalist passes.
| Sponsors | Confirm sponsorships and request logos for the final program.
| Committees | Request final plans from each committee chair.
| Budget | Review and finalize the event's budget.
| Tasks | Build a final task list leading up to the event.
1 month in advance:
| Tickets | Follow up on ticket sales. Call any guests that haven't responded yet.
| Publicity | Place your ads in newspapers, television and radio.
| Staff | Hire staff for the day of the event.
| VIPs | Confirm VIP participation in writing.
| Space planning | Build space diagrams for the room or rooms, build a table plan and assign seats.
| Catering | Provide guest estimate to your caterer, and request a final quote.
| Timeline | Review the timeline for the event, and confirm the scripts with participants.
| Traveling | Organize the traveling arrangements with VIPs.
| Security | Confirm security needs and appoint a security agency.
1 week in advance:
| Meetings | Schedule last-minute meetings with committees. Work out final details.
| Attendance | Confirm final attendance with ticket or table sales.
| Staff | Confirm the staffing for the event. Hire any necessary extra staff.
| Timeline | Provide the timeline to all event participants.
| Catering | Confirm final catering order.
| Beverages | Confirm final alcohol order if not provided by the caterer.
| Media | Confirm media coverage with journalists or stations.
| Rehearsal | Schedule and hold rehearsals if necessary.
| Cheques | Write the cheques that need to be given to providers on the day of the event.
One day before:
| Attire | Lay out your clothes for the event. Prepare a change of clothes in case of emergency.
| Supplies | Verify that all supplies are available or confirm with providers for their delivery time.
Day of the event:
| Arrival | Arrange to arrive early to receive all deliveries and finalize last-minute details.
| Inventory | Make sure that all supplies are on hand.
| Timeline | Confirm scripts and timeline with VIPs.
| Staff | Confirm positions and tasks with staff.
| Technical setup | Make sure the lights and sound are working properly with your technicians.
| Rehearsal | If holding a final rehearsal, have it a few hours before the event, after the sound and lighting have been set up.
Have a great time at your event!
© Checklist.com 2010-2024
https://checklist.com/event-checklist