## Checklist
Level 1 | Level 2 | Notes
Twelve to Eighteen Months Ahead
| Meet with stakeholders | Hold a formal meeting with stakeholders to ensure you understand their needs and are prepared to meet them.
| Book the venue | In larger cities, this may have to be booked even further ahead. Pay the deposit and sign any necessary contracts to ensure the space is reserved.
| Secure funding | Before setting a budget, ensure funding is in place.
Six Months Ahead
| Price catering | Make a shortlist of vendors who meet the menu and budget guidelines to present to committee members or the head organizer.
| Book security | If the event requires security, book now and pay a deposit.
| Key speakers or guests | Book speakers and send save 'the date' notices to key guests.
Eight to Twelve Weeks Ahead
| Designate an event contact | This is the person guests can call or email for information or to RSVP.
| Marketing | Advertise the event in media, online, or by sending invitations for a private function.
| Reserve accommodations | Book a block of hotel rooms near the event venue if out of town guests require.
| Travel | Price train fare and flights and send this information to guests traveling to attend.
| Sponsors | If prizes or gifts are required, solicit donations from community sponsors.
| Audiovisual and seating | Determine audiovisual requirements and a seating arrangement to ensure the seating and equipment is available.
Four Weeks Ahead
| Train staff | Hold a training session for staff to reiterate expectations, set standards, and delegate duties leading up to and the day of the event.
| Licenses | Secure any parking, liquor, or other required licensing.
| Catering | Confirm the menu and number of attendees with the caterer.
| Agenda | Finalize and distribute the agenda to all organizers, speakers, and support/technology staff.
The Week of the Event
| Set-up | Supervise set-up and walk through the days events to ensure all systems are in place, equipment is working, and supplies are adequate.
| Meet with staff | Take staff through the venue and give each a detailed description of their duties.
| Prepare signage | Set up signage, place cards, menu boards, and any other visuals.
| Speakers | Contact each speaker to confirm and review the agenda.
| Entertainment | Confirm live entertainment needs and ensure all equipment is ready.
| Decorate the venue | Buy additional supplies, if needed.
The Day of the Event
| Arrive early | Delegate tasks for all organizers, volunteers, and staff. Oversee the operation as all equipment, seating, signage, etc., are checked.
| Designate greeters | Have an adequate number of staff or volunteers welcome guests and orient them in the space.
| Be available | Carry a cell phone or handset and communicate regularly with staff and volunteer organizers.
After the Event
| Clean up | Return any rented equipment, glassware, or seating.
| Prepare thank you notes | Thank all volunteers, speakers, sponsors, and organizers for their contribution.
| Balance the budget | Prepare a final budget and submit to your organization.
| Summarize the event | Write a report for organization members who may plan similar events in the future.
© Checklist.com 2010-2024
https://checklist.com/event-planner-checklist