## Checklist
Level 1 | Level 2 | Notes
Buying and Ordering
Select apppliances.
Consider how much space you want to allocate to each appliance.
Research ratings and reliability online or in a consumer magazine.
Look at cabinet styles and get preliminary estimates.
Browse countertop options.
Get ideas for any large features you want for your kitchen.
Consider hiring professional kitchen designer.
Begin designing the layout for the room.
Set up a preliminary outline of work to be done.
Begin ordering windows, doors, moldings, appliances, sink, flooring etc.
When ordering ask about delivery times and installation costs.
Sign contracts for cabinets, demolition, installation, and any other renovation work.
Set up a chronological spreadsheet.
Preparation
Rent a trash container.
Set up a working kitchen.
Clean out the kitchen.
Wait for new cabinets and appliances.
Get rid of old appliances and cabinets.
Shut off electricity, then water.
Clean the kitchen and trash area.
Check arrival dates of workers and materials.
Plan to keep the work areas clean daily.
Installation and Decoration
Install base cabinets.
If your appliances are built in, they'll need to be on hand when cabinets are installed.
Install wall cabinets.
Install countertops.
Install backsplash.
| Install the sink, faucets, disposal, and make all water connections | Test for leaks.
Install drawers and doors.
Install matching cabinet end panels and appliance panel covers for dishwashers, refrigerators, and others.
Install or attach lighting fixtures to the ceiling, wall, or under cabinets.
Install flooring.
Clean and polish everything.
Install window treatments.
© Checklist.com 2010-2024
https://checklist.com/kitchen-remodeling-checklist