## Checklist
Level 1 | Level 2 | Notes
Define this shift’s work |  | Use one run per defined work package and crew. Expand the scope only through the approved site plan.
| Identify the project and approved work area | Record the project and exact work area from the current authorized plan.
| Record this shift’s work package | Name the actual activities and package/reference for this crew, including scope boundaries.
| Record the shift briefing time | Enter the actual local date and time of this briefing.
| Identify the authorized site supervisor | Choose the person responsible for the defined work-start decision. Assignment does not grant authority.
| Verify the crew and each responsible lead | Record the approved crew roster or attendance reference, including the relevant trade leads. Do not copy unnecessary personal records.
Review changed conditions and prerequisites |  | The qualified site team supplies hazards, controls and current legal prerequisites.
| Compare current conditions with the previous shift | Record relevant weather, access, work-scope or interface changes and the current assessment reference where useful. Leave the answer blank when there is no additional change to report; the work-area checks still apply.
| Verify the approved method and risk assessment | Check the approved method and assessment revisions against the actual work. Add the reference or a mismatch here when useful; the approved site records remain authoritative and mismatches need the designated authority.
| Verify applicable permits for this shift | Check any permits required by the site procedure for this activity and shift. Add their reference, status, validity/scope and issuer when applicable. Leave blank when no permit is required; this field does not waive an applicable permit.
| Verify crew competence for the assigned work | Have authorized staff check competence against the assigned activities. Add verification references or gaps when useful; assignment alone does not establish competence.
| Verify equipment-release records for the planned activity | For equipment used in this activity, have authorized staff verify the required asset/release status. Add references or unavailable equipment when applicable; leave blank if no equipment-release check is relevant.
| Agree trade interfaces and logistics | Confirm any overlapping work, shared access, deliveries or vehicle/pedestrian interfaces with the relevant leads. Add agreed controls or unresolved conflicts when present; leave blank when none apply.
Walk the actual work area |  | The supervisor tailors these starter checks to the approved work package before briefing. Use the actual site controls; record observations or blockers in task notes.
| Starter check: access route and work-area boundary | Check the authorized route and boundaries against the current plan. Note obstructed access, changed exclusions or conflicting work; do not enter an uncleared area.
| Starter check: shared work and delivery interfaces | Confirm the actual overlap with other trades, vehicle/pedestrian routes and planned deliveries with the coordinating leads. Add an owner for unresolved conflicts.
| Starter check: changed site or weather conditions | Compare the current conditions with the limits and review triggers in the approved site procedure. Ask the qualified lead to reassess changed conditions; this template supplies no generic threshold.
Brief the crew and check understanding |  | Use current approved site information in a language and format the crew understands.
| Brief the actual emergency and reporting arrangements | Brief the actual alarm/reporting method, safe-location arrangements and relevant contacts. Ask the crew to identify the route for this work area. Add the site-information reference or an exception only when useful.
| Ask the crew to explain the key work controls | Ask a practical question about the current work, relevant controls or any important change. Record the response and clarification needed; attendance alone does not establish understanding.
| Record the briefing attendance evidence | The crew is identified in the opening answer. Add a separate attendance-record reference or late-arrival follow-up if needed; do not duplicate an existing crew/attendance record.
Resolve blockers and record the authorized decision |  | A completed checklist is not a permit. Affected work remains on hold until the designated authority clears it.
| Identify every held activity and required clearance | If an activity is held, record its blocker, affected scope, accepted owner and clearance needed; create an open corrective task. Leave blank when no activities are held.
| Record the authorized start or hold decision | Use only the designated site authority’s decision for the identified scope. Keep unsafe or uncleared work on hold.
| Record the actual decision time | Record when the designated authority made the decision for this defined work scope.
| Record the start-or-hold approval reference | Add a supporting approval or clearance reference when the site process requires one, or identify a decision maker different from the supervisor above. The actual decision and time remain separate required answers.
| Communicate the decision to affected crews | Tell affected crews the authorized start or hold scope and any restrictions or re-review trigger. Add a communication reference, exception or next trigger when useful; a routine completed briefing need not be transcribed.
© Checklist.com 2010-2026
https://checklist.com/site-pre-start-checklist